## Sheet1
Agile Test Plan
Project Name | Labrynth Game |  | Engine: | Unity
Team # | 5 |  | Version: | 1
Written By: | Brian Kwapisz & Matt Feret |  | Description: | Maze Game
Log # | Date | Action | Work Involved | Known Bugs/Notes | Complete?
1 | 2016-10-17 | Demo Level | Set-up demo level | N/A
2 | 2016-10-17 | Ball movement | Add PlayerController script | Fine tune ball speed
3 | 2016-10-17 | Camera movement | Add CameraController script | Fine tune height
4 | 2016-10-18 | Create prefabs of walls | Create prefabs for easy lvl gen | N/A
5 | 2016-10-18 | Create additional levels | Copy and stack levels vertically | N/A
6 | 2016-10-18 | Add textures | Add realistic wood textures | Dark wood for floor light wood for walls
7 | 2016-10-18 | Add InGame UI | High score, level display, timer/score | Determine score display/tracking
8 | 2016-10-20 | Add Menu UI | Game title, start button | Working
9 | 2016-10-20 | Add GameOver UI | game over text, restart button, menu button | Bug: Ball falls to last achieved level when restarting
10 | 2016-10-20 | Win and Lose Holes | create object and scripts | Invisible walls needed to prevent ball from going OOB
11 | 2016-10-20 | Vary additional levels | Vary the previously added levels | added variation with escalating difficulty
12 | 2016-10-25 | Debugging Known Issues | fix known bugs | Fixed restart bug, score display, invisible walls
13 | 2016-10-26 | README file | add README to explain controls | n/a
14 | 2016-10-26 | Finishing Touches | Final runthrough, skybox, and bug check | n/a
|  | Date | Tasks Remaining Actual | Tasks Remaining Ideal
|  | 2016-10-13 | 14 | 14
|  | 2016-10-14 | 14 | 13
|  | 2016-10-15 | 14 | 12
|  | 2016-10-16 | 14 | 11
|  | 2016-10-17 | 11 | 10
|  | 2016-10-18 | 7 | 9
|  | 2016-10-19 | 7 | 8
|  | 2016-10-20 | 4 | 7
|  | 2016-10-21 | 4 | 6
|  | 2016-10-22 | 4 | 5
|  | 2016-10-23 | 4 | 4
|  | 2016-10-24 | 4 | 3
|  | 2016-10-25 | 3 | 2
|  | 2016-10-26 | 2 | 1

## Sheet2
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE